## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 2 | 3 | Tech stack setup — Install JDK 21, configure Maven, and create repository structure | Must Have | None | Ramya.S | Completed
Sprint 1 | Sprint 1 | 2 | Integrate logging and configure JDBC connection | Must Have | Task 1 | Ramya.S | Completed
Sprint 1 | Sprint 1 | 3 | Add dependencies for JUnit test cases | Should Have | Task 1 | Ramya.S | Completed
Sprint 1 | Sprint 1 | 4 | Recall exceptions and collections, verify successful project build | Should Have | Task 1 | Ramya.S | Completed
Sprint 1 | Sprint 1 | 5 | Create data models for Customer, Account, and Transaction | Must Have | Task 4 | Ramya.S | Completed
Sprint 1 | Sprint 1 | 6 | Implement Account Service functionality | Must Have | Task 5 | Ramya.S | Completed
Sprint 1 | Sprint 1 | 7 | Explore REST APIs and integrate with backend services | Could Have | Task 6 | Ramya.S | Completed
Sprint 1 | Sprint 1 | 8 | Develop Customer and Account modules | Must Have | Task 6 | Ramya.S | Completed
Sprint 2 | Sprint 2 | 9 | Implement Transaction module | Must Have | Task 8 | Ramya.S | Completed
Sprint 2 | Sprint 2 | 10 | Implement Email Notification service | Could Have | Task 9 | Ramya.S | Completed
Sprint 2 | Sprint 2 | 11 | Implement file download (report generation) feature | Should Have | Task 10 | Ramya.S | Completed
Sprint 2 | Sprint 2 | 12 | Add PIN number feature for transactions | Could Have | Task 9 | Ramya.S | Completed
Sprint 2 | Sprint 2 | 13 | Add UI for better interaction | Could Have | Task 11 | Ramya.S | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
| 1 | Tech stack setup-JDK 21,maven,creating repository structure | 16.08.2025 | 20.08.2025 | Ramya.S | Coding | completed
| 2 | Integration of logging,JDBC Connection Configuration | 19.08.2025 | 19.08.2025 | Ramya.S | Coding | completed
| 3 | Adding dependencies for junit testcases | 20.08.2025 | 20.08.2025 | Ramya.S | Coding | completed
| 4 | Recalling Exceptions,Collections.Checking successful build of project | 21.08.2025 | 21.08.2025 | Ramya.S | Learning | completed
| 5 | creation of datamodels -Customer,Account,Transaction | 22.08.2025 | 26.08.2025 | Ramya.S | Coding | completed
| 1900-01-05 | Account Service Implementation | 29.08.2025 | 11.09.2025 | Ramya.S | Coding | completed
| 1900-01-06 | Exploring REST APIs | 01.09.2025 | 02.09.2025 | Ramya.S | Learning | completed
| 1900-01-07 | Working on Customer and Account modules | 03.09.2025 | 11.09.2025 | Ramya.S | Coding | completed
SPRINT 2 BACKLOG
| 1900-01-08 | Implementing Transaction module | 12.09.2025 | 23.09.2025 | Ramya.S | Coding | completed
| 1900-01-09 | Implementing email service | 25.09.2025 | 29.09.2025 | Ramya.S | Coding | completed
| 1900-01-10 | Implementing sheet download | 06.10.2025 | 07.10.2025 | Ramya.S | Coding | completed
| 1900-01-11 | Adding pin number feature for transaction | 10.10.2025 | 11.10.2025 | Ramya.S | Coding | completed
| 1900-01-12 | Adding UI | 11.10.2025 | 15.10.2025 | Ramya.S | Coding | completed
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Initial Maven setup failed due to missing environment variables | Installed JDK 21 correctly and reconfigured Maven path
Sprint 1 | Day 2 | JDBC connection error while testing | Updated database URL and verified driver in pom.xml
Sprint 1 | Day 3 | JUnit dependency conflict | Re-added correct JUnit 5 dependency and rebuilt project
Sprint 1 | Day 4 | Account model not saving data properly | Debugged service layer and fixed constructor issue
Sprint 1 | Day 5 | Console logger not printing formatted output | Adjusted logger configuration file and verified output
Sprint 2 | Day 1 | Transaction module validation logic failing | Reviewed validation rules and corrected conditional checks
Sprint 2 | Day 2 | Email service not sending messages | Added proper SMTP settings and tested with mock data
Sprint 2 | Day 3 | Report file download not triggered | Fixed file path in ReportService and tested CSV generation
Sprint 2 | Day 4 | UI not updating after transaction | Bound data refresh to event listener in controller
Sprint 2 | Day 5 | PIN feature verification delays | Created test cases to validate PIN before transaction execution

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-08-16 | 2025-09-11 | Ramya S | Setting up complete tech stack and using Maven for builds | Manual project builds and untracked changes | Following coding standards and Git version control | Maven integration and repository structured; all initial setup completed
2 | Sprint 1 | 2025-08-16 | 2025-09-11 | Ramya S | Applying logging and JDBC connectivity | Ignoring error logs | Writing clean, reusable service code | Logging successfully configured and verified
3 | Sprint 1 | 2025-08-16 | 2025-09-11 | Ramya S | Practicing exception handling and test cases | Delaying small bug fixes | Using JUnit for validation | All exceptions tested and handled properly
4 | Sprint 2 | 2025-09-12 | 2025-10-11 | Ramya S | Implementing functional modules like Transaction and Email service | Working without predefined API structure | Modular coding and consistent commits | Transaction and Email modules fully implemented
5 | Sprint 2 | 2025-09-12 | 2025-10-11 | Ramya S | Adding UI components and extra features (PIN, reports) | Last-minute UI fixes | Enhancing project based on feedback | UI and additional features added and tested
6 | Sprint 2 | 2025-09-12 | 2025-10-11 | Ramya S | Planning retrospection after each sprint | Skipping documentation | Maintaining agile documentation regularly | Retrospection and agile docs updated
7 | Sprint 2 | 2025-09-12 | 2025-10-14 | Ramya S | Reviewing test coverage and optimizing code | Unreviewed commits | Team code review and refactoring | Project optimized and all modules tested