## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ramya | 2025-10-08 | Transaction API returning 500 error | Sprint 2 | Backend Team | Functional | Fixed missing parameter in POST request | 2025-10-09 | Closed | Verified after retest
2 | Ramya | 2025-10-09 | UI not updating after successful transaction | Sprint 2 | Frontend Team | UI/Logic | Added useEffect hook to trigger state update | 2025-10-10 | Closed | Working fine in QA
3 | Ramya | 2025-10-10 | Duplicate transaction entries generated | Sprint 2 | Database Team | Data Integrity | Added unique constraint on transaction ID | 2025-10-11 | Closed | No duplicates observed
4 | Ramya | 2025-10-11 | API timeout during fund transfer | Sprint 2 | Backend Team | Performance | Optimized API response and increased timeout | 2025-10-12 | Closed | Verified
5 | Ramya | 2025-10-12 | Transaction logs not updating in real-time | Sprint 2 | Backend Team | Functional | Implemented WebSocket for live updates | 2025-10-13 | Closed | Verified by QA
6 | Ramya | 2025-10-13 | Wrong timestamp showing in history | Sprint 2 | Backend Team | Data Format | Converted timestamps to UTC | 2025-10-14 | Closed | Consistent now
7 | Ramya | 2025-10-14 | Null pointer error during validation | Sprint 2 | Backend Team | Code Defect | Added null checks before field access | 2025-10-15 | Closed | Stable in test

## Sheet2
Logical
User Interface
Maintainability
Standards
Others